## Read Me
Migration administration workbook
Helper-script Desktop sign-in to interactive Entra browser sign-in, then evidence-gated Cosmos projection switch.
Section | Purpose | Owner output
Inputs | Enter gateway, Entra and change-window values. Blue text/yellow fill marks administrator inputs. | Approved values
Dashboard | Formula-driven go/no-go state from mandatory preflight rows. | GO only after PASS or N/A
Roles | Azure, Entra, Graph, Intune and network handoffs. | Named owners
Preflight | Read-only checks with evidence. | Signed evidence
Sign-in Migration | Backup, public-client app, recorded external-idp choice, accepted audience and generated policy. | Pilot-ready sign-in
Intune Rollout | Deterministic Windows policy deployment and pilot. | Successful pilot
Projection Cutover | Preflight, clean compare, full-sync evidence, dry-run and one-write switch. | projection source
Verify-Rollback | Post-change proof and independent rollback paths. | Closure/restoration
Commands | Formula-generated command templates from Inputs. | Reviewed commands
Intune Scripts | Current MDM guide script templates. | Upload package
References | Repository evidence for each procedure. | Audit trail
Safety boundary | Named values remain authoritative until the final switch. Desktop sign-in and entitlement source are separate changes with separate rollback paths.

## Inputs
Operator inputs
Replace placeholders before copying generated commands.
Input | Value | Source / validation
Repository root | C:\path\to\claude-code-foundry-gateway | Current clone
Subscription ID | <subscription-id> | az account show
Tenant ID | <tenant-id> | az account show
Resource group | <resource-group> | Existing APIM resource group
APIM name | <apim-name> | Existing gateway
Projection prefix | <lowercase-prefix> | 1-37 lowercase letters/digits
Location | eastus | Resource group / Cosmos region
APIM SKU | StandardV2 | BasicV2, StandardV2 or PremiumV2
Resolver inbound access | private | BasicV2 public; Standard/Premium default private
Resolver application ID | <resolver-app-id> | Selected or created app
Standard group | claude-code-standard | Gateway-recorded group
Premium group | claude-code-premium | Gateway-recorded group
Desktop app display name | Claude Desktop gateway | Public-client registration
Desktop client ID | <desktop-public-client-id> | App script output
Desktop issuer | https://login.microsoftonline.com/<tenant-id>/v2.0 | App script output
Intune pilot group | <pilot-group> | Approved small pilot
Azure operator | <name> | Change owner
Entra administrator | <name> | App/consent owner
Intune administrator | <name> | MDM owner
Change window UTC | <yyyy-mm-dd hh:mm> | Approved record
Backup path | <generated-after-phase-1> | Gateway backup output

## Dashboard
Migration dashboard
Complete every mandatory preflight row before live changes.
Overall decision | INCOMPLETE
Failed checks | 0
Incomplete checks | 16
Passed checks | 0
N/A checks | 0
Gate | Required evidence | Rule
Desktop app readiness | Client ID, issuer, redirect URI and consent decision | Before pilot
Intune pilot | Device/User status succeeded and Desktop restarted | Before switch
Projection compare | Clean comparison; named values remain authoritative | Required
Full sync evidence | Successful full sync within 24 hours | Required
Dry-run switch | Resolver, drift, runner compare and evidence pass | Required
Live switch | Backup path; entitlement-source reads projection | Final write

## Roles
Roles and handoffs
Azure subscription roles and Entra directory roles are separate.
Role | Responsibility | Required access | Named owner
Azure operator | Backup, named value, deploy, compare and switch | Resource deployment; APIM named-value read/write; resolver config; runner start/exec | <name>
Entra application administrator | Desktop public client and consent | Application registration and tenant consent authority | <name>
Entra group reader | Directory snapshot for compare/sync | GroupMember.Read.All full sync; User.ReadBasic.All targeted | <name>
Intune administrator | Pilot and assign managed settings | Configuration, platform script or Remediations | <name>
Network administrator | Private resolver network approval | VNet/subnet/private DNS join/write | <name>
Change approver | GO/NO-GO and rollback authority | Organization change process | <name>

## Preflight
Mandatory preflight
Read-only checks. Select PASS, FAIL or N/A and attach redacted evidence.
# | Check | Command / place | Pass criterion | Owner | Status | Evidence / ticket
1 | Repository and PowerShell | git status; $PSVersionTable.PSVersion | Correct repo; PowerShell 7+ | Azure operator
2 | Azure context | az account show | Subscription/tenant match Inputs | Azure operator
3 | Current source | Read entitlement-source | named-value | Azure operator
4 | Current Desktop audience | Read external-idp-extra-audience | Value recorded for rollback | Azure operator
5 | Gateway backup | Backup-ClaudeGateway.ps1 | Backup file exists | Azure operator
6 | Desktop app preview | New-ClaudeDesktopEntraApp.ps1 -WhatIf | App/redirect approved | Entra admin
7 | Consent policy | Entra review | Pilot consent path approved | Entra admin
8 | Projection preflight | Deploy-ClaudeProjection.ps1 -PreflightOnly | No FAIL; exit 0 | Azure operator
9 | Tier groups | Preflight output | Recorded groups resolve exactly | Entra admin
10 | Resolver registration | Preflight output | Selected app or creation allowed | Entra admin
11 | Providers | Preflight output | Required providers registered | Azure operator
12 | Names | Preflight output | Valid/available or reusable | Azure operator
13 | Network path | Network review | Approved public/private shape | Network admin
14 | Intune pilot | Intune group review | Small pilot approved | Intune admin
15 | Rollback authority | Change record | Named owner | Approver
16 | Change window | Change record | Approved communications/window | Approver

## Sign-in Migration
Desktop sign-in migration
Backup, create/discover public client, record external-idp browser, write one audience named value and regenerate profiles.
# | Step | Action / command | Expected result | Owner | Status | Evidence / output
1 | Create/discover Desktop app | Run Commands row 4 after preview passes. | clientId, tenantId, issuer and redirect returned | Entra admin | NOT STARTED
2 | Consent decision | Review tenant user-consent policy. | No AADSTS65001 blocker for pilot | Entra admin | NOT STARTED
3 | Back up handover | Copy onboarding/claude-gateway.json with UTC suffix. | Helper-script record preserved | Azure operator | NOT STARTED
4 | Record external-idp | Set kind external-idp, flow browser, id_token issuer/clientId. | ClaudeDesktopSignIn validation passes | Azure operator | NOT STARTED
5 | Write audience | Set external-idp-extra-audience to client ID. | Read-back exact match | Azure operator | NOT STARTED
6 | Generate standard policy | New-ClaudeCodePolicy.ps1 -Tier standard. | Payloads generated | Azure operator | NOT STARTED
7 | Generate premium policy | New-ClaudeCodePolicy.ps1 -Tier premium. | Payloads generated | Azure operator | NOT STARTED
8 | Review policy | Confirm gateway and interactive Desktop keys. | Azure/Intune sign-off | Azure + Intune | NOT STARTED

## Intune Rollout
Intune pilot rollout
Use deterministic HKLM writers, pilot first and monitor before broad assignment.
# | Step | Action / command | Expected result | Owner | Status | Evidence / output
1 | Choose delivery | Platform script, Remediation or Win32 unless matching ADMX/CSP exists. | Deterministic method | Intune admin | NOT STARTED
2 | Claude Code package | Embed exact generated JSON using Intune Scripts. | HKLM ClaudeCode Settings written | Intune admin | NOT STARTED
3 | Detection | Calculate exact Settings SHA-256. | Exit 0 only on exact match | Intune admin | NOT STARTED
4 | Desktop package | Bundle generated claude-desktop.reg. | Direct HKLM Claude values | Intune admin | NOT STARTED
5 | Script settings | System context; 64-bit; signature per policy. | Correct registry view | Intune admin | NOT STARTED
6 | Pilot assignment | Assign only to Inputs pilot group. | Correct tier payload | Intune admin | NOT STARTED
7 | Restart Desktop | Fully quit/reopen. | Browser sign-in shown | Pilot | NOT STARTED
8 | Functional pilot | Sign in and send request. | Gateway accepts client-id audience | Pilot + Azure | NOT STARTED
9 | Monitor | Retain Device/User status. | Pilot succeeded | Intune admin | NOT STARTED

## Projection Cutover
Cosmos projection cutover
Deploy/compare while named values serve. Switch only after fresh full-sync evidence and clean -WhatIf.
# | Step | Action / command | Expected result | Owner | Status | Evidence / output
1 | Projection preflight | Commands row 9. | All checks pass; no writes | Azure operator | NOT STARTED
2 | Deploy/populate/compare | Commands row 10. | Clean comparison message | Azure operator | NOT STARTED
3 | Full sync evidence | Commands row 11. | Success within 24h | Azure operator | NOT STARTED
4 | Dry-run switch | Commands row 12. | All evidence passes; no write | Azure operator | NOT STARTED
5 | GO/NO-GO review | Attach compare/sync/dry-run evidence. | Approver authorizes one write | Approver | NOT STARTED
6 | Live switch | Commands row 13. | Backup; source=projection | Azure operator | NOT STARTED
7 | Read-back | Commands row 14. | Exact projection value | Azure operator | NOT STARTED
8 | One-user proof | Targeted sync after approved group change. | User published | Azure operator | NOT STARTED
9 | Post-check | Full sync and test request. | No unexpected refusal; success | Azure operator | NOT STARTED

## Verify-Rollback
Verification and rollback
Desktop and projection rollback are independent. Refresh/compare named values before source rollback.
# | Step | Action / command | Expected result | Owner | Status | Evidence / output
1 | Desktop policy | Managed keys show external-idp/browser and client ID. | Verified | Intune admin | NOT STARTED
2 | Desktop request | Pilot sign-in and gateway response. | Verified | Pilot + Azure | NOT STARTED
3 | CLI continuity | Claude Code/VS Code still use Azure CLI. | Verified | Pilot | NOT STARTED
4 | Projection source | entitlement-source reads projection. | Verified | Azure operator | NOT STARTED
5 | Targeted publication | -User updates changed identity. | Verified | Azure operator | NOT STARTED
6 | Desktop rollback | Restore record/audience; regenerate/deploy helper profile. | When sign-in fails | Azure + Intune | NOT STARTED
7 | Named-value refresh | Sync-ClaudeAccess.ps1 -Store named-value. | Lists refreshed | Azure operator | NOT STARTED
8 | Named-value compare | Compare-ClaudeEntitlement.ps1 -FailOnDrift. | No drift | Azure operator | NOT STARTED
9 | Source rollback | Set entitlement-source=named-value after 7-8. | Named values serve | Azure operator | NOT STARTED
10 | Close change | Attach backups and evidence. | Record complete | Approver | NOT STARTED

## Commands
Generated command templates
Review placeholders and optional arguments before running.
# | Purpose | Command | Expected output
1 | Azure context | az account show --query "{subscription:id,tenant:tenantId,user:user.name}" -o json az account set --subscription "<subscription-id>" | Context matches
2 | Read entitlement source | az apim nv show -g "<resource-group>" --service-name "<apim-name>" --named-value-id entitlement-source --query value -o tsv | named-value
3 | Preview Desktop app | pwsh -NoProfile -File .\scripts\New-ClaudeDesktopEntraApp.ps1 -DisplayName "Claude Desktop gateway" -WhatIf | No writes
4 | Create/discover Desktop app | pwsh -NoProfile -File .\scripts\New-ClaudeDesktopEntraApp.ps1 -DisplayName "Claude Desktop gateway" | App object
5 | Write Desktop audience | . .\scripts\ApimNamedValue.ps1 Set-ApimNamedValue -ResourceGroup "<resource-group>" -ApimName "<apim-name>" -Id external-idp-extra-audience -Value "<desktop-public-client-id>" | Exact client ID
6 | Generate standard policy | pwsh -NoProfile -File .\scripts\New-ClaudeCodePolicy.ps1 -ConfigPath .\onboarding\claude-gateway.json -Tier standard -OutputPath .\policy-claude-code-standard | Payload files
7 | Generate premium policy | pwsh -NoProfile -File .\scripts\New-ClaudeCodePolicy.ps1 -ConfigPath .\onboarding\claude-gateway.json -Tier premium -OutputPath .\policy-claude-code-premium | Payload files
8 | Projection arguments | -SubscriptionId "<subscription-id>" -ResourceGroup "<resource-group>" -ApimName "<apim-name>" -NamePrefix "<lowercase-prefix>" -Location "eastus" -Sku "StandardV2" -ResolverInboundAccess "private" -ResolverAppId "<resolver-app-id>" -StandardGroup "claude-code-standard" -PremiumGroup "claude-code-premium" | Remove unneeded optional args
9 | Projection preflight | pwsh -NoProfile -File .\scripts\Deploy-ClaudeProjection.ps1 -SubscriptionId "<subscription-id>" -ResourceGroup "<resource-group>" -ApimName "<apim-name>" -NamePrefix "<lowercase-prefix>" -Location "eastus" -Sku "StandardV2" -ResolverInboundAccess "private" -ResolverAppId "<resolver-app-id>" -StandardGroup "claude-code-standard" -PremiumGroup "claude-code-premium" -PreflightOnly | No FAIL
10 | Deploy/populate/compare | pwsh -NoProfile -File .\scripts\Deploy-ClaudeProjection.ps1 -SubscriptionId "<subscription-id>" -ResourceGroup "<resource-group>" -ApimName "<apim-name>" -NamePrefix "<lowercase-prefix>" -Location "eastus" -Sku "StandardV2" -ResolverInboundAccess "private" -ResolverAppId "<resolver-app-id>" -StandardGroup "claude-code-standard" -PremiumGroup "claude-code-premium" | Clean comparison
11 | Full sync | pwsh -NoProfile -File .\scripts\Sync-ClaudeAccess.ps1 -ResourceGroup "<resource-group>" -ApimName "<apim-name>" | Success evidence
12 | Dry-run switch | pwsh -NoProfile -File .\scripts\Deploy-ClaudeProjection.ps1 -SubscriptionId "<subscription-id>" -ResourceGroup "<resource-group>" -ApimName "<apim-name>" -NamePrefix "<lowercase-prefix>" -StandardGroup "claude-code-standard" -PremiumGroup "claude-code-premium" -FlipAfterCleanCompare -WhatIf | All checks; no write
13 | Live switch | pwsh -NoProfile -File .\scripts\Deploy-ClaudeProjection.ps1 -SubscriptionId "<subscription-id>" -ResourceGroup "<resource-group>" -ApimName "<apim-name>" -NamePrefix "<lowercase-prefix>" -StandardGroup "claude-code-standard" -PremiumGroup "claude-code-premium" -FlipAfterCleanCompare | Backup and one write
14 | Read source | az apim nv show -g "<resource-group>" --service-name "<apim-name>" --named-value-id entitlement-source --query value -o tsv | projection
15 | Targeted sync | pwsh -NoProfile -File .\scripts\Sync-ClaudeAccess.ps1 -ResourceGroup "<resource-group>" -ApimName "<apim-name>" -User "<upn-or-object-id>" | User result
16 | Rollback refresh | pwsh -NoProfile -File .\scripts\Sync-ClaudeAccess.ps1 -ResourceGroup "<resource-group>" -ApimName "<apim-name>" -Store named-value | Lists refreshed
17 | Rollback compare | pwsh -NoProfile -File .\scripts\Compare-ClaudeEntitlement.ps1 -ResourceGroup "<resource-group>" -ApimName "<apim-name>" -FailOnDrift | No drift

## Intune Scripts
Intune script templates
Windows PowerShell 5.1-compatible templates from docs/MDM.md.
Script / setting | Content
Platform settings | Run using logged-on credentials: No Signature: organization policy; No unless signed 64-bit host: Yes
Claude Code install/remediation | $ErrorActionPreference = 'Stop' $settings = @' <paste claude-code.managed-settings.json as one JSON document> '@ $key = 'HKLM:\SOFTWARE\Policies\ClaudeCode' New-Item -Path $key -Force ¦ Out-Null New-ItemProperty -Path $key -Name Settings -PropertyType String -Value $settings -Force ¦ Out-Null
Claude Code detection | $expected = '<sha256 of the exact Settings string>' $value = (Get-ItemProperty -Path 'HKLM:\SOFTWARE\Policies\ClaudeCode' -Name Settings -ErrorAction SilentlyContinue).Settings if (-not $value) { exit 1 } $sha = [System.Security.Cryptography.SHA256]::Create() try { $bytes = $sha.ComputeHash([System.Text.Encoding]::UTF8.GetBytes($value)) } finally { $sha.Dispose() } $actual = -join ($bytes ¦ ForEach-Object { $_.ToString('x2') }) if ($actual -eq $expected) { exit 0 } exit 1
Claude Code rollback | $key = 'HKLM:\SOFTWARE\Policies\ClaudeCode' Remove-ItemProperty -Path $key -Name Settings -ErrorAction SilentlyContinue if (Test-Path $key) { $remaining = Get-ItemProperty -Path $key if ($remaining.PSObject.Properties.Name -notcontains 'Settings') { Remove-Item -Path $key -Recurse -Force -ErrorAction SilentlyContinue } }
Claude Desktop import | $ErrorActionPreference = 'Stop' reg.exe import .\claude-desktop.reg if ($LASTEXITCODE -ne 0) { throw "Claude Desktop policy import failed: $LASTEXITCODE" } # Package generated .reg beside script; fully quit/reopen Desktop.
Desktop location | HKLM\SOFTWARE\Policies\Claude; values directly under key; object/array values are JSON strings; subkeys ignored.
OMA-URI caution | Use ./Device/Vendor/MSFT/Policy/Config/ClaudeCode/Settings only with matching custom ADMX/Policy CSP. Otherwise use script, Remediation or Win32.

## References
Repository references
Current sources used for this workbook.
Source | Supports | Path
Secure projection | Preflight, compare, sync evidence, switch and rollback capacity | SECURE-PROJECTION.md
Update and change | Manual Desktop sign-in change | UPDATE-AND-CHANGE.md#5-change-claude-desktop-sign-in
Developer guide | Browser/broker config and consent | ../DEVELOPER.md#letting-desktop-do-the-sign-in-itself
MDM guide | Generated outputs and Intune scripts | MDM.md
Projection workbook | Role separation | PROJECTION-WORKBOOK.md
Desktop app script | Public-client creation/discovery | ../scripts/New-ClaudeDesktopEntraApp.ps1
Policy generator | Managed policy generation | ../scripts/New-ClaudeCodePolicy.ps1
Projection deployer | Current params and switch behavior | ../scripts/Deploy-ClaudeProjection.ps1
Sync command | Publication to active store | ../scripts/Sync-ClaudeAccess.ps1
Compare command | Named values vs Entra drift | ../scripts/Compare-ClaudeEntitlement.ps1
Desktop sign-in ADR | Choice and consequences | adr/0027-claude-desktop-sign-in-choice.md